## Sheet1
s/n | page | task | detais | assing person | status | comment
| 10 | shipping address print | we need this label on customer bag as a tiny invoice and sending address and scan this when send for delivery | Partho
| 10 | SKU/Product Code | From product list print sku and product code print from list | akbor
| 11 | Menu list | Admin menu | Partho | Done
| 12 | Dashboard | dashbor desing and details | Partho | done
| 13 | Quick Report | Desing and development | akbor | 20% | only desing
| 13 | Order history | Details of orders | Partho
| 14 | Pending order | Pending order list, print, process, Edit and cancel | akbor + Patho | Done
| 15 | Process | Process order list, print, Edit and cancel | Partho | Done
| 16 | Dispatch | Dispactch list , delivery, Edit | Partho | working on Edit
| 17 | excel dispath | excel dispath list, copy, complete | akbor+partho |  | details required (Copy pending)
| 17 | Delivery Invoice | Searchng, List and details | Partho
| 18 | Delivery | List, print, Edit and cancel | akbor+partho | in edit shiping address
| 18 | cancel | List, Print edit | akbor | Done | Edit Details Requried
| 19 | All status | List, Print Edit | akbor | Done | Edit Detail Info Requred
| 20 | Send percel | List, srach | Partho
| 21 | Reject | list |  |  | details required
| 22 | stock | list,print,Edit and delete | Partho
| 23 | Reject item | Remove | Partho |  | details required
| 23 | Best customer | List | Partho
| 24 | Gross Profit | List | Partho
| 24 | Gross Profit summer | List | Partho